## Completed Actions
| Environmental Sustainability Actions and timetable | September
| Action | Notes | Completed Date
1 | Make changes to the council's own premises, people and services we deliver
1.1.1 | Draw up carbon assessment tool to be to assess all council projects | COMPLETE - In use | 2020
1.1.2 | Undertake initial review of current EH sustainability purchasing statements included within existing service contracts to determine effectiveness and relevance. | COMPLETE - Our Contract Procedure Rules now ensure that procurement is conducted in a sustainable manner, taking environmental impact into account. The guidelines ask consideration of: do you really need it, can you specify a product service or works that is inherently more sustainable and that evaluation of the sustainability of the delivery of the goods works or service is undertaken. | 2020-05-01
1.1.4 | Explicitly refer to sustainability outcomes in MTFP from 2020/21 budget onwards | COMPLETE - Now standard element of council's budget planning. | 2020
1.1.5 | Amend the council’s procurement regulations to explicitly include consideration of carbon footprint (a) the determination of whether to procure (b) the specification for good and/or services to be procured and (c) the quality assessment of competing tenders. | COMPLETE - Contract procedure rules amended. | 2020
1.3 | Carry out a staff survey to gather ideas for environmental sustainability | COMPELTE - 9 ideas were already in the Action Plan. Of the remainder, (24/69) 35% have been created as specific additional line items. The remainder, are already either complete, incorporated within a wider Action Plan line item or can be dealt with outside of the Action Plan. | 2020
1.4.4 | WALLFIELDS - Replace light fittings with LED | COMPELTE - Full replacement in December 2020. | 2020-12-01
1.4.5 | WALLFIELDS - Review Local Authority decarbonisation grant scheme | COMPLETE - Investigated but oversubscribed. | 2020
1.5.4 | BUNTINGFORD - Review Local Authority Decarbonisation Grant Scheme | COMPLETE - Investigated but oversubscribed. | 2020
1.6.1 | Audit current numbers of/need for e-chargers across all carparks | COMPLETE - Audit information now informing installation works across all carparks. | 2020-05-01
1.6.2.0 | NORTHGATE END - (Bishop's Stortford) Investigate opportunities for installation of solar canopy on top deck. | COMPLETE - August 2021. Viability of taking this forward has been investigated. While there are no plans at present to install a solar canopy, we will remain vigilant regarding inward investment opportunities to take this forward. | 2021-09-01
1.6.2.1 | NORTHGATE END - Investigate opportunities for maximising sustainability during construction. | COMPLETE - May 2021 - A wet woodland incorporating over 300 shrubs and trees has been planted to the side of the car park providing biodiversity enhancement to the area. 54 e-chargers and LED lighting will be installed on completion. | 2021-05-01
1.7.1 | Investigate/procure 100% low-carbon electricity | COMPLETE - From 1st April 2021, when our energy accounts as part of CCS framework swap from British gas to EDF, we will be placed on their Blue for Business tariff which used 100% low carbon energy. This exercise has gone partially beyond the original existing EDF contracts i.e. 19 rather than 4 contracts and includes the BG electricity contracts which are for smaller site e.g. toilets so is a positive move. The intention once further contract renegotiation is possible is to look to move to 100% renewable. | 2021-04-01
1.8.1 | GRANGE PADDOCKS - Maximise environmental opportunities sustainability through the tender evaluation process. | COMPLETE - Tender specification fully reviewed | 2020
1.8.2 | GRANGE PADDOCKS - Investigate opportunities for Solar PV installation | COMPLETE - These are now installed (April 2021) and producing 16.38kW at peak levels. | 2020-04-01
1.9.1 | HARTHAM - Maximise environmental sustainability opportunities through the tender evaluation process. | COMPLETE - Works commenced | 2020-02-01
1.12.3 | Undertake energy saving improvement at the Hillcrest Council- owned hostel | All common parts and individual flats have been retrofitted with LED replacements in recent years. | 2020
1.12.4 | Undertake energy saving improvement at the Rectory Council- owned hostel | COMPELTE - Since the property was purchased in 2020, the main building has been improved by replacement hot water boilers, new thermostatic and on/off controls to existing radiators, LED lights throughout and movement sensors in all common parts. The Annex and Cedar Cottage (now converted into six new bedsits for single homeless people) has LED lights, two new gas boilers from a previous three, communal heating systems, replacement double glazing from single and thermal loft, floor and ceiling insulation. Revised EPC certificate requested to calculate savings. | 2020-04-01
1.15 | Assess evidence-base for benefits of green walls | COMPLETE - Incorporated into the Sustainability Supplementary Planning Document (SPD) which was passed at full council in March 2021. | 2021-03-01
1.17 | Maximise environmental sustainability opportunities through Hertford Hydro | The Executive Committee has now considered the updated business case for the Hydro and have determined that alternative investments elsewhere will be more beneficial to environmental sustainability and climate change progress. | 2021-07-01
1.18.1 | Introduce video-conferencing technology in council buildings | COMPLETE - Q3 2020 (FY) | 2020
1.19 | Confirm Terms of Reference for Environmental Sustainability Corporate Group with a view to include wider sustainability issues beyond immediate carbon measures. | COMPLETE - Beyond carbon accounting, this Action Plan now incorporates the following terms : - Waste/Recycling - Land use/agriculture/Biodiversity - Energy/water/resources - Housing and planning - Business and Economic Development - Transport | 2021-04-01
2 | Use regulatory powers to promote action by others
2.1.1 | Publish an Environmental Sustainability SPD Climate declaration - climate friendly planning and building control regulations | COMPLETE - Agreed at Full Council 2nd March 2021 and now published on East Herts Council website. | 2021-03-01
2.3 | Survey locally active residential developers to better understand barriers to higher energy efficiency/Passivhaus development | COMPLETE - Results of survey provided useful information. HCCSP Carbon Group is looking to develop actions around upskilling of contractors on a County-wide basis. | 2020
2.4.1 | Understanding the sign off process and ensuring sustainability gains in relation to the ambitions of the climate change Action Plan are facilitated in future s106 agreements | COMPLETE - All proposed planning permissions where s106 is triggered are now notified to Environmental Sustainability. The sign off process and stakeholders for the different types of allocations are known and work is underway to embed environmental sustainability personnel and factors more closely into the decision making process, potentially through the development of a check list. | 2021-09-01
2.6 | Install anti-idling guidance/advisory signage in council carparks. | COMPLETE - A Clean Air Day campaign was rolled out across East Herts and materials shared with other Hertfordshire Local Authorities. 26 anti-idling signs were also installed in car parks across East Herts. | 2021-06-01
3 | Influence and encourage others to do things
3.2 | Climate Declaration - Establish and run a multi-agency/stakeholder Environmental and Climate Forum meeting every two months and ensure Action Plan is updated on a monthly basis and made available to the public via our website. | COMPLETE - Now established and meeting every two months with different themes per meeting. The Action Plan is updated on a monthly basis and shared on our website. | 2020
3.3.1.1 | Investigate options to sign up to Queen's Canopy Project once officially launched in May. | COMPLETE - East Herts marked the launch of the Queens Canopy initiative on 24th May via a Council staff volunteering day. This saw us plant over 300 native trees and shrubs at Northgate End in Bishop’s Stortford, creating a ‘wet woodland’ in the heart of the town, accessible to everyone. Contact with HCC (who are holding a database of trees planted) is also established and work is underway to publish further promotional information to Parish/Town Councils and community groups. | 2021-09-01
3.5.1 | Write to ministers to initiate dialogue about powers and freedoms to support delivery of climate change commitments | COMPLETE - The Leader of the Council wrote to the Secretary of State in January 2020 requesting further support in achieving the stated climate change aims. | 2020
3.9 | Install more bicycle racks in the five market towns | The three, two tier cycle racks originally sited in Hertford, Buntingford and Bishop’s Stortford have had to be relocated to support school community active travel for students and staff resulting in Richard Hale, Ward Freeman and Bishop’s Stortford High School being pleased to accept these 16 bike rack storage facilities. Sawbridgeworth Cycle rack in Bell Street is in the process of being made more accessible and will be repositioned slightly to enable this. The new Ware site at Burgage Lane is being re-purposed to accommodate the rack, enabling good travel connections with the new medical centre, Ware High Street and the canal cycleways. | 2021-05-01
3.15 | Hertford Subways AQMA project | COMPLETE - Subways now opened. Some minor works to be completed e.g. relocation of the litter bin. | 2020
3.17.2 | Integrate sustainability topics within the agenda for East Herts Parish Council meetings. | COMPLETE - First meeting to be held in June 21 with sustainability continuing to part of the ongoing agenda. | 2021-06-01

## September update
On a monthly basis, this Action Plan is updated, reviewed by an internal Carbon and Sustainability Steering Committee and published on our website.
On a bi-monthly basis it is reviewed by attendees of our public facing Environmental Sustainability Forum.
| Environmental Sustainability Actions and timetable | Next update | September | Waste & Recycling | Land use, agriculture, biodiversity | Energy, water, resources | Housing & planning | Business & economic development | Transport | Carbon assessment (Old - see comments) | Support East Herts District 2030 carbon neutral target | Council becomes carbon neutral by 2030
Action plan terms of reference
Action
1 | Make changes to the council's own premises, people and services we deliver
1.1 | Climate Declaration - Account for climate impacts in decision-making process | Headline | - | ü | ü | ü | ü | ü | ü |  |  | ü
1.1.1 | Draw up carbon assessment tool to assess all council projects | Complete | COMPLETE - In use | ü | ü | ü | ü | ü | ü |  |  | ü
1.1.2 | Undertake initial review of current EH sustainability purchasing statements included within existing service contracts to determine effectiveness and relevance. | Complete | COMPLETE - Our Contract Procedure Rules now ensure that procurement is conducted in a sustainable manner, taking environmental impact into account. The guidelines ask consideration of: do you really need it, can you specify a product service or works that is inherently more sustainable and that evaluation of the sustainability of the delivery of the goods works or service is undertaken. | ü | ü | ü | ü | ü | ü
1.1.3 | Engagement with main contractors to understand their current commitments towards carbon reduction | 2021-10 | All internal contracts over £5k have been identified. The list will now be prioritised and relationship managers contacted to start the carbon and sustainability audit via common questions. | ü | ü |  |  | ü
1.1.4 | Explicitly refer to sustainability outcomes in MTFP from 2020/21 budget onwards | Complete | COMPLETE - Now standard element of council's budget planning. | ü |  | ü | ü | ü | ü |  |  | ü
1.1.5 | Amend the council’s procurement regulations to explicitly include consideration of carbon footprint (a) the determination of whether to procure (b) the specification for good and/or services to be procured and (c) the quality assessment of competing tenders. | Complete | COMPLETE - Contract procedure rules amended. | ü | ü | ü | ü | ü | ü |  |  | ü
1.2 | Climate Declaration - Train members & officers to promote carbon neutral policies | Headline | - | ü | ü | ü | ü | ü | ü
1,2,1 | Train officers in climate change and sustainability through bite-sized training session. | 2021-10 | 15 sessions have taken place with a total of 101 staff having been trained so far. 4 further sessions are scheduled from September through November 2021. | ü | ü | ü | ü | ü | ü |  |  | ü
1.2.2 | Train Senior Officers in climate change and use of carbon assessment methodology. | 2021-11 | Senior Officers will be trained once the Officer training programme is complete. | ü | ü | ü | ü | ü | ü |  |  | ü
1.2.3 | Offer Member training in sustainability and climate change. | 2022 | Members will be trained once the Senior Officers training is complete. | ü | ü | ü | ü | ü | ü |  |  | ü
1.2.4 | Visits to sustainability sites for the purpose of learning from best practice examples | 2021-10 | Two site visits to sustainable landowner farms have now taken place. More will be arranged now restrictions have lifted. | ü | ü | ü | ü | ü | ü |  |  | ü
1.3 | Carry out a staff survey to gather ideas for environmental sustainability | Complete | COMPLETE - 9 ideas were already in the Action Plan. Of the remainder, (24/69) 35% have been created as specific additional line items. The remainder, are already either complete, incorporated within a wider Action Plan line item or can be dealt with outside of the Action Plan. | ü |  | ü |  |  | ü |  | ü | ü
1.4 | WALLFIELDS - Target EPC rating C Within programme to increase minimum EPC rating of estate over the next three years. | 2021-10 | Will not be progressed until after Agile Working building requirements are established. All staff will be working on a 50:50 home:office ratio from end of September 21 |  |  | ü | [5 empty] | ü
1.4.1 | WALLFIELDS - Audit to inform retrofit / re-fit programme | 2021-10 | Will not be progressed until after Agile Working building requirements are established. All staff will be working on a 50:50 home:office ratio from end of September 21 |  |  | ü | [5 empty] | ü
1.4.2 | WALLFIELDS - Review and action repairs to improve insulation of windows | 2021-10 | New action from staff survey. To be commenced alongside building requirements associated with Agile working |  |  | ü | [5 empty] | ü
1.4.3 | WALLFIELDS - Investigate opportunities for renewable energy generation | 2021-10 | Will not be progressed until after Agile Working building requirements are established. All staff will be working on a 50:50 home:office ratio from end of September 21 |  |  | ü | [5 empty] | ü
1.4.4 | WALLFIELDS - Replace light fittings with LED | Complete | COMPLETE - Full replacement in December 2020. |  |  | ü | [5 empty] | ü
1.4.5 | WALLFIELDS - Review Local Authority decarbonisation grant scheme | Complete | COMPLETE - Investigated but oversubscribed. |  |  | ü | [5 empty] | ü
1.5 | BUNTINGFORD - Target EPC rating C Within programme to increase minimum EPC rating of estate over the next three years. | 2021-10 | Awaiting update. Re-arrange meeting. |  |  | ü | [5 empty] | ü
1.5.1 | BUNTINGFORD - Audit to inform retrofit / re-fit programme | 2021-10 | Awaiting update. Re-arrange meeting. |  |  | ü | [5 empty] | ü
1.5.2 | BUNTINGFORD - Replace light fittings with LED | 2021-10 | Awaiting update - Last update, all LEDs have been replaced in the top shed and work is almost complete in the offices and warehouses. |  |  | ü | [5 empty] | ü
1.5.3 | BUNTINGFORD - Investigate opportunities for renewable energy generation | 2021-10 | Awaiting update - Last update - Contract renewal in 2028 is unlikely to hinder sustainable investments. Facilities Management contacting landlord to gauge thoughts on solar panels on the Southern slopes of the two roofs and having air source heat pump units in cages on the sides of buildings. |  |  | ü | [5 empty] | ü
1.5.4 | BUNTINGFORD - Review Local Authority Decarbonisation Grant Scheme | Complete | COMPLETE - Investigated but oversubscribed. |  |  | ü | [5 empty] | ü
1.6 | CAR PARKS - Investigate carbon reduction and environmental opportunities. | 2021-10 | 95% of all surface level carparks and lamp columns in parks have been fitted with energy efficient bulbs. G-Way MSCP and Jackson Square will be addressed on a replacement basis. The full project is part of our 5 year internal programme. |  |  | ü |  |  | ü
1.6.1 | Audit current numbers of/need for e-chargers across all carparks | Complete | COMPLETE - Audit information now informing installation works across all carparks. |  |  | ü |  |  | ü
1.6.2.0 | NORTHGATE END - (Bishop's Stortford) Investigate opportunities for installation of solar canopy on top deck. | Complete | COMPLETE - August 2021. Viability of taking this forward has been investigated. While there no plans at present to install a solar canopy, we will remain vigilant regarding inward investment opportunities to take this forward. |  |  | ü | [5 empty] | ü
1.6.2.1 | NORTHGATE END - Investigate opportunities for maximising sustainability during construction. | Complete | COMPLETE - May 2021 - A wet woodland incorporating over 300 shrubs and trees has been planted to the side of the car park providing biodiversity enhancement to the area. 54 e-chargers and LED lighting will be installed on completion. | ü |  | ü
1.6.2.2 | NORTHGATE END - Install e-chargers appropriate to demand identified during audit. | 2022-05 | Northgate end will be a 597-space multi-storey car park once complete. 54 e-chargers are confirmed for installation. Completion is anticipated in early May 2022. |  |  | ü |  |  | ü
1.6.3 | GASCOYNE WAY - (Hertford) Install e-chargers appropriate to demand identified during audit. | 2021-10 | Awaiting costs for 2 new fast chargers. |  |  | ü |  |  | ü
1.6.3.1 | GASCOYNE WAY - Green Wall | 2021-10 | Project has previously been examined and external funding sought but unable to obtain. Opportunities for fresh funding are being kept under review and in particular potential for DEFRA Air Quality Grant later in the year subject to Grant funding criteria once known.
1.6.4 | LINK ROAD - (Bishops Stortford) Install e-chargers appropriate to demand identified during audit. | 2021-10 | The opportunity for chargers at Link Road has been investigated and is feasible but confirmation on future configuration of the site is being sought. |  |  | ü |  |  | ü
1.6.5 | BELL STREET - Install e-chargers appropriate to demand identified during audit. | 2021-10 | Easement between town council and East Herts now signed. Work has commenced to install cabling and infrastructure. |  |  | ü |  |  | ü
1.7 | Investigate opportunities for use of 100% renewable energy for council estate | Headline | - |  |  | ü | [5 empty] | ü
1.7.1 | Investigate/procure 100% low-carbon electricity | Complete | COMPLETE - From 1st April 2021, when our energy accounts as part of CCS framework swap from British Gas (BG) to EDF, we will be placed on their Blue for Business tariff which used 100% low carbon energy. This exercise has gone partially beyond the original existing EDF contracts i.e. 19 rather than 4 contracts and includes the BG electricity contracts which are for smaller sites e.g. toilets, so is a positive move. The intention once further contract renegotiation is possible is to look to move to 100% renewable. |  |  | ü
1.7.2 | Investigate potential opportunity to procure 100% low carbon gas | 2022 | Green Gas is gas from lower fossil fuels, i.e. waste biogas. It currently has limited availability in the UK. Evaluate again in 2022 |  |  | ü | [5 empty] | ü
1.7.3 | Install LEDs at all external lamp columns on Council's own estate. | 2022 | 95% of all surface level carparks and lamp columns in parks have been fitted with energy efficient bulbs. G-Way MSCP and Jackson Square will be addressed on a replacement basis. The full project is part of our 5 year internal programme. |  |  | ü | [5 empty] | ü
1.8 | GRANGE PADDOCKS - Achieve BREEAM Excellent standard at new development | Headline | - |  |  | ü | [5 empty] | ü
1.8.1 | GRANGE PADDOCKS - Maximise environmental opportunities sustainability through the tender evaluation process. | Complete | COMPLETE - Tender specification fully reviewed |  |  | ü | [5 empty] | ü
1.8.2 | GRANGE PADDOCKS - Investigate opportunities for Solar PV installation | Complete | COMPLETE : These are now installed (April 2021) and producing 16.38kWhr at peak levels. |  |  | ü | [5 empty] | ü
1.83 | GRANGE PADDOCKS - Investigate opportunities for Heat Recovery | 2021-10 | 520kW has been calculated to be the instantaneous peak electrical demand of the leisure centre i.e. the maximum instantaneous electrical demand. 27% of this is an estimate of the typical minimum electrical demand. Therefore, 27% of 520kW = 140kW. The PV has a peak output of 16.38kW or 16.38 kilo-Joules per second (rate of flow of energy). The CHP (an electricity generator where the heat produced by the engine is recovered and can be used to heat the building) has a peak output, estimated at 50KW, given the calculation currently provided: total (PV+CHP) generation = 66.38kW. 520kW is likely to be an overestimate to ensure that there is enough supply. However, 140kW is more than twice 66.38kW, so it is unlikely that any significant amount of the generated electricity will need to be exported outside the building i.e. exported to the Grid Note if gas is no longer desirable for CHP it can be run off hydrogen in the future. |  |  | ü | [5 empty] | ü
1.84 | GRANGE PADDOCKS - Installation of EV charger(s) | 2021-10 | These will be installed at the end of the programme - 1 point with 2 car capacity in Car Park C and 7 more passive in Car Park B |  |  | ü |  |  | ü |  | ü | ü
1.85 | GRANGE PADDOCKS - Review contractor utilisation of water, energy and resource use throughout the build process in line with BREEAM requirements. | 2021-10 | There is no BREEAM requirement on the project. Environmental Sustainability contribution is tightly monitored, however. Construction Waste diverted from landfill and water consumption are ahead of target. Energy consumption is slightly higher than target due to the project having to be connected to a generator as the permanent power is now routed to the main building and we cannot run our TBS at the same time. The main building is on a 'low carbon' energy tariff. On previous site monitoring, environmental performance has been running at top marks (9/9) - see details on previous plan updates. Excess carbon production will be offset by the carbon offset scheme used by the construction company. They have funded boreholes and low carbon stoves in Uganda and plan to plant 10,000 trees during 2021. |  |  | ü | [5 empty] | ü
1.9 | HARTHAM - Achieve BREEAM Excellent standard for new development | 2021-10 | Pool works are nearing completion and the extension works will start thereafter. Completion is programmed for early December 2022. The building is being designed to reduce thermal gain (orientation and window location/sizes – passive design measures), lighting is specified to be very energy efficient (LEDs), and PVs and/or heat pumps will be specified which will provide a carbon reduction for the building. |  |  | ü | [5 empty] | ü
1.9.1 | HARTHAM - Maximise environmental sustainability opportunities through the tender evaluation process. | Complete | COMPLETE - Works commenced |  |  | ü | [5 empty] | ü
1.9.2 | HARTHAM - Calculate carbon reduction from reduced thermal gain | 2021-10 | New sub action for further reporting. Meeting held with Project Manager in August. Awaiting updates from contractor to enable calculations. |  |  | ü | [5 empty] | ü
1.9.3 | HARTHAM - Calculate carbon reduction from installing LEDs throughout | 2021-10 | New sub action for further reporting. Meeting held with Project Manager in August. Awaiting updates from contractor to enable calculations. |  |  | ü | [5 empty] | ü
1.9.4 | HARTHAM - Calculate carbon reduction from solar PV installation | 2021-10 | New sub action for further reporting. Now we have figures for the PV energy contribution, carbon saving calculations can be undertaken. |  |  | ü | [5 empty] | ü
1.9.5 | HARTHAM - Calculate carbon reduction from air source heat pump installation | 2021-10 | New sub action for further reporting. Meeting held with Project Manager in August. Awaiting updates from contractor to enable calculations. |  |  | ü | [5 empty] | ü
1.9.6 | HARTHAM - Calculate carbon reduction from heat recovery technology | 2021-10 | New sub action for further reporting. Figures received for the heat recovery contribution are being verified prior to undertaking carbon saving calculations. |  |  | ü | [5 empty] | ü
1.9.7 | HARTHAM - Calculate carbon reduction from green wall installation | 2021-10 | New sub action for further reporting. Meeting held with Project Manager in August. Awaiting updates from contractor to enable calculations. |  |  | ü | [5 empty] | ü
1.9.8 | HARTHAM - Audit current number of/need for e-chargers and install more. | 2021-10 | Arrangements for future EV charging are in place and implementation on the ground will be as the building programme permits. |  |  | ü |  |  | ü |  | ü | ü
1.10 | HERTFORD THEATRE - Achieve BREEAM Excellent standard for new development | 2022 | BREEAM excellent rating is sought with an estimated 58% carbon emissions reduction anticipated on completion in 2023. Building energy use intensity will reduce 444 Wh/m2 per year to 260 Wh/m2 per year or, using benchmarking data, from 0.667kg to 0.334kg of CO2 per customer. These numbers are particularly significant as the building area, occupancy and energy consumption will increase when completed. |  |  | ü | [5 empty] | ü
1.10.1 | HERTFORD THEATRE - Maximise environmental sustainability through the planning and tender evaluation process. | 2021-10 | Planning was granted in March 21 and contractor tendering has commenced with appointment anticipated in October. Works will commence soon after for planned completion in April 2023. Awaiting update on contractor appointment |  |  | ü | [5 empty] | ü
1.10.2 | HERTFORD THEATRE - Calculate carbon reduction replacement of gas boilers by air source heat pumps for heating/cooling. | 2021-11 | New sub action for further reporting once contractor specification is known - late 21. |  |  | ü | [5 empty] | ü
1.11 | Maximise opportunity for EV - own and contract fleet | Headline | - | [5 empty] | ü |  |  | ü
1.11.1 | Incentivise use of e-car pool by officers | 2021-10 | E-pool cars are now being used by officers and a new, Covid-safe protocol is in place. The cars will potentially be used as trial vehicles by officers moving diesel to e-vans or cars. Updated promotional material is now on our website (Sept) and planning for further promotion via social media is underway. | [5 empty] | ü | Current saving by EV pool car scheme vehicles: 14tCO2e pa | ü | üü
1.11.2 | Audit the council's vans with a view to replacing them with e-vehicles | 2021-10 | Development of the full business case for replacement is underway. Evaluation includes the future required numbers, mileage ranges and capacity of vehicles, e-charging requirement and purchase/lease options. Meeting also held with the Energy Saving Trust regarding EV “fleet” comparison including larger (RCV) vehicle. | [5 empty] | ü | Conversion of all council vans to EV would save approx. 49tCO2 pa | ü | üü
1.12 | Evaluate and monitor opportunities for sustainability improvements through East Herts Housing Association owned properties. | Headline | - |  |  | ü | ü
1.12.1 | Publish a new Housing Strategy for 2021 - 2026 incorporating environmental sustainability measures. | 2021-12 | A new housing strategy will be presented to Full Council in December 21. It will contain a section on Housing and Sustainability and the Sustainability Team are actively involved in its development. | ü | ü | ü | ü | ü | ü
1.12.2 | Millstream to conduct EPC ratings for existing housing stock. | 2021-10 | All current EPCs for Millstream’s properties plus a list of energy efficiency works conducted to date are in the process of being collated. A possible "master action", to utilise Millstream to deliver carbon efficient development is under consideration. |  |  | ü | ü |  |  |  | ü
1.12.3 | Undertake energy saving improvement at the Hillcrest Council- owned hostel | Complete | All common parts and individual flats have been retrofitted with LED replacements in recent years. |  |  | ü
1.12.4 | Undertake energy saving improvement at the Rectory Council- owned hostel | Complete | Since the property was purchased in 2020, the main building has been improved by replacement hot water boilers, new thermostatic and on/off controls to existing radiators, LED lights throughout and movement sensors in all common parts. The Annex and Cedar Cottage (now converted into six new bedsits for single homeless people) has LED lights, two new gas boilers from a previous three, communal heating systems, replacement double glazing from single and thermal loft, floor and ceiling insulation. Revised EPC certificate requested to calculate savings. |  |  | ü
1.12.5 | Monitor and report on Housing Association energy efficiency programmes | 2021-11 | An energy efficiency programme is currently being undertaken with the 15 housing associations who build, own and/or manage housing stock in East Herts. High quality sustainable development standards are encouraged including the Housing Quality Mark (HQM) (equivalent to BREEAM) Passivhaus and Building Futures - an interactive Hertfordshire guide to promoting sustainability in development. A record of all Associations' environmental sustainability actions will also be compiled. |  |  | ü
1.13 | Utilise Eastern New Energy ERDF Scheme to deliver innovative, low carbon sustainability projects. | 2021-10 | Initial introductory meeting held with University of East London who are leading the Eastern New Energy scheme. Various elements are underway such as a grant scheme for businesses in relation to energy and sustainability. |  |  | ü |  | ü |  |  | üü
1.13.1 | Assess opportunities and possible benefits of establishing an energy 'White Label'. | 2021-10 | Initial introductory meeting held with University of East London - project leads for Eastern New Energy. Awaiting further update. |  |  | ü |  | ü |  |  |  | ü
1.13.2 | Assess options for work in partnership to operate an energy services company to deliver potential carbon offset opportunities. | 2021-10 | Initial introductory meeting held with University of East London - project leads for Eastern New Energy. The regional initiative is under investigation. This is a 2021 - 23 scheme. Further promotion/reporting in October |  |  | ü |  | ü |  |  | üüü
1.14 | Continue to develop sustainable options for waste and recycling | Headline | - | ü |  |  |  |  | ü |  |  | ü
1.14.1 | Work with Hertfordshire Waste Partnership partners and others to explore synergies of working across administrative boundaries | 2023 | Pending contract change point in 23/24 | ü |  |  |  |  | ü |  | ü
1.14.2 | Consider reducing domestic residual waste bins to 140 litre capacity to 'nudge' more recycling | 2023 | To be explored with the new contracts in 2023/24. Looking at more efficient ways of collecting waste. Action - Maximising gains from contract renewals. | ü | [5 empty] | Data required to estimate carbon saving and to determine effect on increased recycling collection | ü
1.14.3 | Explore potential and practicality of electric refuse vehicles | 2021-10 | We will be able to contractually change our fleet in 2025. Meantime investigations into the potential and practicality of electric refuse vehicles are underway - breakeven/ round service mileage, depot implications and an ECollect electric vehicle demonstration/meeting with the Sustainability team in October 21. | ü |  |  |  |  | ü
1.15 | Assess evidence-base for benefits of green walls | Complete | COMPLETE - Incorporated into the Sustainability Supplementary Planning Document (SPD) which was passed at full council in March 2021. |  | ü | ü |  |  | ü |  |  | ü
1.16 | Investigate opportunities for improving biodiversity of council estate and associated services. | 2021-10 | May 2021 marked the launch of The Queens Green Canopy campaign which will invite community groups, charities, schools, councils and landowners to plant trees to commemorate the Queens Platinum Jubilee in 2022 and enhance our environment and the landscape, for generations to come. We marked the launch on 24th May via a Council staff volunteering day, which saw us plant over 300 trees and shrubs at Northgate End in Bishop’s Stortford, creating a ‘wet woodland’ in the heart of the town, accessible to everyone. Planning for further tree planting and community engagement is underway with tree contributions already in place via donations from Julie Marson (MP) and the Association of Jewish Refugees (AJR) |  | ü | ü | [5 empty] | ü
1.16.1 | Work with HCC and others to identify options for tree planting | 2021-10 | A database of tree planting relating to the Queens Canopy is now administered by Hertfordshire County Council. Hertfordshire has a target for 3200 tree plantings shared equally between the 10 Local Authorities. East Herts is keeping a tally of tree plantings in district and is currently on target. Work to promote the Queens canopy to Town and Parish Councils and community groups is also underway. Further opportunities will also come about once HCCSPs biodiversity land audit takes place. |  | ü |  |  |  |  | Carbon sequestration: 0.157tCO2/50 years per tree. Note: varies by spp; site; planting; management . Existing EHC tree stock estimated at 220tCO2pa | üü | ü
1.17 | Maximise environmental sustainability opportunities through Hertford Hydro | Complete | COMPLETE - The Executive Committee has now considered the updated business case for the Hydro and have determined that alternative investments elsewhere will be more beneficial to environmental sustainability and climate change progress. |  | ü | ü
1.18 | Maximise opportunities to utilise IT infrastructure (back and front end) to further carbon reduction. | Headline | - |  |  | ü | [5 empty] | ü
1.18.1 | Introduce video-conferencing technology in council buildings | Complete | COMPLETE - Q3 2020 (FY) |  |  | ü |  |  | ü |  |  | ü
1.19 | Confirm Terms of Reference for Environmental Sustainability Corporate Group with a view to include wider sustainability issues beyond immediate carbon measures. | Complete | COMPLETE - Beyond carbon accounting, this Action Plan now incorporates the following terms : - Waste/Recycling - Land use/agriculture/Biodiversity - Energy/water/resources - Housing and planning - Business and Economic Development - Transport | ü | ü | ü | ü | ü | ü |  |  | ü
1.20 | Incorporate HCCSP Water plans etc. | 2021-10 | We are planning on completing the insertion of these new actions once the revised drafts of the action plans become available. |  |  | ü | [5 empty] | ü
1.21 | Work to improve biodiversity infrastructure on Council estate. | 2022-01 | Environmental Sustainability and Biodiversity considerations are a core part of the Parks and Open Spaces Strategy 21-26, which will be approved/published in Jan 2022. Ongoing strategy work with CMS ensures all planned park projects optimise biodiversity as well as s106 contribution opportunities. The Queens Canopy initiative is being factored into the open space strategy. We are also mindful of the forthcoming HCCSP Land Audit and the intel that will provide towards required future schemes. |  | ü | [6 empty] | ü
1.21.1 | Incorporate relevant actions from HCCSP biodiversity Action Plan within this Action Plan. | 2021-10 | We are planning on completing the insertion of these new actions once the revised drafts of the action plans become available. |  | ü | [6 empty] | ü
2 | Use regulatory powers to promote action by others | [9 empty] | ü | ü
2.1 | Climate declaration - climate and sustainability friendly planning and building control regulations. Seek to develop appropriate planning policy to further establish climate change and sustainability ambitions. | Headline | - |  | ü | ü | ü |  |  | Carbon assessment analysis possible once draft guidance produced. Potential for significant savings | üüü
2.1.1 | Publish an Environmental Sustainability SPD | Complete | COMPLETE - March 21 - Agreed at Full Council and now published on East Herts Council website: | ü | ü | ü | ü |  | ü |  | ü
2.1.2 | Publish a Vehicle Parking Standards SPD | 2021-12 | Production planning is underway for a new Vehicle Parking in New Development SPD (to replace the current Vehicle Parking Standards SPD) which will include requirements for vehicle charging points etc. The provisional timetable plans for consultation in late 21 with adoption in early 2022. |  |  | ü | ü |  | ü |  | ü
2.1.3 | Publish a Biodiversity SPD. | 2022-01 | Yet to commence. Planned for 2022 |  | ü |  | ü |  |  |  | ü
2.1.4 | Publish a revised District Plan | 2021-10 | A District Plan review is due to start in the autumn 2021, with a ‘call for sites’. | ü | ü | ü | ü | ü | ü
2.2 | Develop sustainability advice geared towards listed buildings / conservation areas | 2021-10 | East Herts has over 4000 Listed Buildings. Meeting held with planning colleagues and all associated current guideline documentation now reviewed. A number of listed buildings are held by agricultural landowners in East Herts. An opportunity to connect planning with this community is under development for the next Rural Round Table. |  |  | ü | ü |  |  | Carbon assessment analysis possible once draft guidance produced. Potential for significant savings | üü
2.3 | Survey locally active residential developers to better understand barriers to higher energy efficiency/Passivhaus development | Complete | COMPLETE - Results of survey provided useful information. HCCSP Carbon Group is looking to develop actions around upskilling of contractors on a County-wide basis. |  |  | ü | ü |  |  | No. Passivhaus in planning? Carbon saving calculation possible | ü
2.4 | Utilise s106 to maximise interventions in order to facilitate the Council's sustainability ambitions. | 2021-10 | Work is progressing well on identifying potential sustainability opportunities (project themes and locations) that could be fulfilled via s106 contributions. Next internal meeting in September. | ü | ü | ü | ü | ü | ü | Interventions can be carbon assessed. Potential for positive savings | üü
2.4.1 | Understanding the sign off process and ensuring sustainability gains in relation to the ambitions of the climate change Action Plan are facilitated in future s106 agreements | Complete | COMPLETE - All proposed planning permissions where s106 is triggered are now notified to Environmental Sustainability. The sign off process and stakeholders for the different types of allocations are known and work is underway to embed environmental sustainability personnel and factors more closely into the decision making process, potentially through the development of a check list. | ü | ü | ü | ü | ü | ü |  | ü
2.4.2 | Investigate 'unallocated' sums with a view to working with recipients to provide guidance and encouragement to ensure use of funds is related as far as possible to sustainability ambitions of the Council. | 2021-10 | Work is progressing well on identifying potential sustainability opportunities (project themes and locations) that could be fulfilled via s106 contributions. Next internal meeting end of September. | ü | ü | ü | ü | ü | ü |  | ü
2.4.3 | Produce 'shopping list' for actions which can be assisted and achieved through s106 agreements i.e. village hall improvements and e-charging | 2021-10 | Meetings and 'sustainable shopping lists' will be developed upon completion of the analysis of existing s106 contribution potential. | ü | ü | ü | ü | ü | ü |  | ü
2.4.4 | Work with HCC Transport to review existing funds/projects and future allocations to ensure facilitation of the Council's climate and sustainability ambitions with a joined up approach. | 2021-10 | Initial meeting between HCC Transport and East Herts Sustainability Team held in May. Our s106 Manager also attends regularly scheduled meetings with HCC to ensure potential and existing project awareness around sustainability is ongoing. | [5 empty] | ü |  | ü
2.5 | Maximise environmental sustainability through the Harlow Gilston Garden Town Development | Headline | - | ü | ü | ü | ü | ü | ü | Carbon assessment analysis possible once draft guidance produced. Potential for significant savings | üüü
2.5.1 | Identify and meet Harlow Gilston sustainability leads and develop co-ordinated action. | 2021-10 | East Herts influence is predominantly around planning. Meeting held with Planning and legal colleagues around forwarding the sustainability agenda and wording development guidelines. In the meantime we will maintain a watching brief. | ü | ü | ü | ü | ü | ü |  | ü
2.6 | Install anti-idling guidance/advisory signage in council carparks. | Complete | COMPLETE - A Clean Air Day campaign was rolled out across East Herts and materials shared with other Hertfordshire Local Authorities. 26 anti-idling signs were also installed in car parks across East Herts. |  |  | ü |  |  | ü
2.6.1 | Work with HCC on introducing enforcement measures in relation to anti-idling. | 2021-10 | In contact with HCC. Potential for a county-wide campaign coming through HCCSP. East Herts have conducted their own research into the legalities and possibilities. |  |  | ü |  |  | ü |  | ü
2.7 | Facilitate move to increased use of e-taxis through promotion of Herts 2025 EV Taxi Scheme. | 2021-10 | MHCLG has confirmed an ERDF scheme final go ahead and project is being led by Electric Blue with support from Herts Local Authorities. We will be working with Electric Blue to promote the scheme to the East Herts licensed taxi trade. |  |  | ü |  | ü | ü |  | ü
2.7.1 | Install rapid e-chargers in support of move to more e-taxis. | 2021-10 | Installation planning underway. Anticipated numbers to be reported here in October following procurement discussions with potential contractor. |  |  | ü |  | ü | ü | Carbon savings can be measured once scheme underway | ü
2.7.2 | Review and update taxi vehicle policies to further strengthen incentives/requirements for low emission taxis | 2021-10 | Currently being investigated by HCCSP transport group. |  |  | ü |  | ü | ü | No.taxis by emission standard versus proposed improvements/ carbon calculation possible | üü
2.8 | Work to utilise regulatory powers to facilitate improved domestic energy efficiency measures. | 2021-11 | The 2021-26 Housing Strategy has aim to formally evaluate domestic EPC levels across the district, which will inform gaps and potential. All EPCs of housing coming to market are already regularly collected. A general trend of improvement has been noted. |  |  | ü |  |  |  |  | ü
2.8.1 | Consider promoting improved EPC ratings through HMO licensing powers and policies. | 2021-10 | Part of this action is being taken forward via the East Herts Housing Strategy 2021-2026 under the theme Housing Standards and Environmental Sustainability . The Clean Growth Strategy set a target to upgrade as many houses to EPC Band C by 2035 “where practical, cost-effective and affordable”, and for all fuel poor households, and as many rented homes as possible, to reach the same standard by 2030. A list of all HMO landlords, available in the public domain, will also be used for a direct marketing campaign promoting EPC improvements. |  |  | ü |  |  |  | No. HMO/current EPC values? Carbon saving calculation possible
| Explore a pilot to incentivise EPC A properties through the council tax system | Complete | COMPLETE - Reviewed and concluded not to take forward. Will retain for review. Determined other methods to incentivise domestic energy efficiency. |  |  | ü |  |  |  |  | ü
3 | Influence and encourage others to do things | [9 empty] | ü
3.1 | Provide and promote energy efficiency grants/support | 2021-10 | Looking to develop further domestic energy assistance schemes in the future and are examining a range of options including grants, loans and Government funding opportunities. Local enquiries have recently increased after a period of levelling off May through July. |  |  | ü |  |  |  | Estimated at up to 800 tCO2 saving if move from gas to oil. Actuals unknown, as move to gas for first time heating may increase CO2 depending on current heating method/size of property. Home insulation measures can be assessed for carbon benefits and will be positive benefit. | ü
3.2 | Climate Declaration - Establish and run a multi-agency/stakeholder Environmental and Climate Forum meeting every two months and ensure Action Plan is updated on a monthly basis and made available to the public via our website. | Complete | COMPLETE - Now established and meeting every two months with different themes per meeting. The Action Plan is updated on a monthly basis and shared on our website. | ü | ü | ü | ü | ü | ü
3.3 | Enhance biodiversity infrastructure across the District | Headline | - |  | ü | [5 empty] | ü
3.3.1 | Work with community to explore and action tree planting | 2021-10 | Plan underway to inform Town & Parish Councils about the Queens Canopy initiative and to identify sites suitable for tree planting/enhancement. Some interest has already been expressed by a number of Parish/Town Councils. |  | ü | [5 empty] | ü
3.3.1.1 | Investigate options to sign up to Queen's Canopy Project once officially launched in May. | Complete | COMPLETE - East Herts marked the launch of the Queens Canopy initiative on 24th May via a Council staff volunteering day. This saw us plant over 300 native trees and shrubs at Northgate End in Bishop’s Stortford, creating a ‘wet woodland’ in the heart of the town, accessible to everyone. Contact with HCC (who are holding a database of trees planted) is also established and work underway to publish further promotional information to Parish/Town Councils and community groups. |  | ü | [5 empty] | ü
3.3.1.2 | Consider opportunities to establish an 'adopt a tree pit' scheme. | 2022 | Yet to commence. Will involve working with Highways and residents regarding adopting a tree outside their property. |  | ü | [5 empty] | ü
3.3.2 | Enable volunteers to come together on joint initiatives (information, co-ordination and training) | 2021-10 | A number of community-led sustainability events are taking place across the district in the run up to COP26 in November 21. EHDC is supporting these events by creating an inter-town network where we connect people and ideas as well providing a channel for promotion and potential grant funding. The monthly Get Involved calendar on our website also continues to provide events and ideas for community groups and individuals. |  | ü | [5 empty] | ü
3.3.2.1 | Consider opportunities to establish community wildlife areas, for example, adjacent to play areas | 2021-10 | High-level discussions held with CMS. Checking opportunities with Wellbeing team. |  | ü | [5 empty] | ü
3.3.2.2 | Work with Parish Councils to promote local biodiversity action. | 2021-10 | The intention for East Herts to take a greater co-ordinating role in sustainability matters was introduced at the first Town & Parish Council Engagement Event in June. Engagement will commence with promotion of the Queens Canopy initiative. |  | ü | [5 empty] | ü
3.3.2.3 | Work with HCC to ensure appropriate management of highways verges for biodiversity. | 2022 | Some verges are now not mowed where safety permits. Further work to be informed by the HCCSP biodiversity audit. |  | ü | [5 empty] | ü
3.4 | Establish improved dialogue with rural and farming community | Headline | - |  | ü | [5 empty] | ü
3.4.1 | Establish and run a Rural Round Table bringing together key stakeholders in the farming and land holding/owning community. | 2021-10 | The first Rural Round Table was held in February. Planning for a second meeting is now underway and will incorporate some of the actions arising from the first meeting and objectives taken from HCCSP and East Herts Action Plans. |  | ü | [5 empty] | ü
3.5 | Climate declaration Call on National Government for more powers and resources | Headline | - | ü | ü | ü | ü | ü | ü |  | ü
3.5.1 | Write to ministers to initiate dialogue about powers and freedoms to support delivery of climate change commitments | Complete | COMPLETE - The Leader of the Council wrote to the Secretary of State in January 2020 requesting further support in achieving the stated climate change aims. | ü | ü | ü | ü | ü | ü |  | ü
3.5.2 | Work with local MPs to promote the case for investment in sustainability interventions in East Herts | 2021-10 | Officers met with two local MPs. Future meetings to be organised in due course. | ü | ü | ü | ü | ü | ü
3.6 | Climate Declaration - Work with partners - District, County and Region | 2021-10 | Hertfordshire Climate Change and Sustainability Partnership (HCCSP) Biodiversity, Transport and Water plans will be integrated into East Herts Action Plan once completed and agreed by HCCSP. They are currently in draft and pending consideration of feedback from consultees. We are planning on completing the insertion of these new actions once the revised drafts of the action plans become available. | ü | ü | ü | ü | ü | ü |  | ü
3.7 | Run EV roadshows and demonstrations - at least one a year | 2021-10 | An e-car and e-bicycle display will be available at the Hertford Green Festival on 25th September in Hertford town centre. Further possibilities are being explored for other community sustainability events and festivals in the run up to COP26 in November. |  |  | ü |  |  | ü |  | ü
3.8 | Run two climate change film festivals (Hertford and Stortford) | 2021-10 | Previously delayed by COVID, these film viewings are now taking place as part of community-led sustainability events across the district in the run up to COP26 in November 21. Film is a confirmed element of Bishops Stortford's and Sawbridgeworth's event and possibilities are being explored in Herford and Ware also. | ü | ü | ü | ü | ü | ü
3.9 | Install more bicycle racks in the five market towns | Complete | The three, two tier cycle racks originally sited in Hertford, Buntingford and Bishop’s Stortford have had to be relocated to support school community active travel for students and staff resulting in Richard Hale, Ward Freman and Bishop’s Stortford High School being pleased to accept these 16 bike rack storage facilities. Sawbridgeworth Cycle rack in Bell Street is in the process of being made more accessible and will be repositioned slightly to enable this. The new Ware site at Burgage Lane is being re-purposed to accommodate the rack, enabling good travel connections with the new medical centre, Ware High Street and the canal cycleways. | [5 empty] | ü
3.10 | Incentivise the public to make more use of the council e-car pool | 2021-10 | The scheme has now been fully re-opened to the public and promotion is now in place on our website. Further promotion will be arranged via social media. |  |  | ü |  |  | ü
3.11 | Hold a Schools Climate Conference | 2021-10 | Now Covid restrictions are lifting, development of ideas are recommencing. This action was originally planned for 2022 but the team have started re-engagement with schools via campaigns around Clean Air Day, ModeSHIFT Stars, World Car Free Day, Great Big Green week and tips for getting children involved with carbon and waste reduction and sustainability initiatives. A schools conference is potentially being arranged by HCC as part of the COP26 programme. | ü | ü | ü | ü |  | ü
3.12 | Work with Bishop's Stortford BID and other business groups to promote sustainability | 2021-10 | Meeting held with Bishop Stortford's BID Manager on 8th September 21. Agreed a joint campaign to promote sustainability related grants for businesses (Business Climate Hub, Workplace Charging Scheme, Low Carbon Workspace campaign and the Eastern Energy Grant) via direct email, web and social media channels |  |  |  |  | ü |  | Carbon saving calculation possible once details provided | ü
3.13 | Create East Herts awards scheme to encourage local organisations, neighbourhoods and individuals to implement sustainable activities | 2021-10 | The Bishop Stortford Independent has been approached with a view to facilitating the award scheme for delivery in line with COP26. East Herts are investigating other possibilities for finding 'environmental champions' (individuals and groups) via their own social channels. | ü | ü | ü | ü | ü | ü |  | ü
3.14 | Actively implement and encourage waste minimisation initiatives | 2021-10 | International Compost Awareness Week, Love Parks (Keep Britain Tidy) and Plastic Free July were promoted via our Get Involved calendar. The East Herts' Master Composting initiative has generated an encouraging number of community volunteers now specifically trained in food waste reduction. July's Environmental and Climate Forum covered Waste and Recycling and Recycling September is now being actively promoted via our social media channels. | ü | [5 empty] | Data required to estimate carbon saving and to determine effect on increased recycling collection | üü
3.15 | Hertford Subways AQMA project | Complete | COMPLETE - Subways now opened. Some minor works to be completed e.g. relocation of the litter bin. | [5 empty] | ü |  | ü
3.16 | PARISH COUNCILS AND VILLAGE HALLS - explore creation of rural EV charging hub network based on parish owned sites | 2021-10 | Positive responses from 5 parish councils/village halls received so far. Further engagement took place at East Herts-wide Town and Parish Council meeting in June. Now identifying potential installation opportunities via s106 funding - next meeting end of September. |  |  | ü |  |  | ü |  | ü
3.17 | Work with Parish Councils and Village Halls on sustainability initiatives | 2021-10 | Potential projects and town/village locations have been identified as part of our ongoing evaluation of s106 funding availability. Engagement with individual town/parish councils and village hall representatives has commenced with a wider approach, perhaps via a combined meeting, under consideration. |  | ü | ü |  |  | ü |  | ü
3.17.1 | Explore creation of 'sustainable shopping list' for village hall equipment upgrades where s106 funding exists. | 2021-10 | Now potential project themes and town/village locations have been identified the framework for a shopping list is available. Work will commence following a go-ahead meeting in September. |  |  | ü |  |  | ü |  | ü
3.17.2 | Integrate sustainability topics within the agenda for East Herts Parish Councillors Conference. | Complete | COMPLETE - The sustainability topic has now been confirmed as a regular entry on the agenda at this meeting. | ü | ü | ü | ü | ü | ü |  | ü
3.20 | Smart approach to publicity | 2021-10 | Starting with internal activity we have developed a schedule of blogs, written by members of our sustainability working group, that will be published monthly via our internal communications email and stored on our Intranet. A staff survey will also take place in September 21 to gauge staff environmental interest(s), and which will enable targeted staff engagement so that we can deliver the Sustainable part of SEED - 'sustainability being at the heart of everything we do.' Our Clean Air Day campaign touched 11,000 residents and had a 6 times greater rate of engagement than other recent social media posts. A next wave of promotion covering sustainability grants and initiatives for businesses, use of our e-vehicles and engagement with COP26 is in planning. | ü | ü | ü | ü | ü | ü |  | üü
3.20.1 | Review and expand web site pages on environmental sustainability, climate change and energy efficiency to provide enhanced advice and encourage behaviour change to promote positive climate action | 2021-10 | Analysis of web-visitor metrics to the sustainability pages is now complete. Further work is underway to enable more granular reporting and further uplift visitor numbers. Work underway includes making Sustainability accessible from the East Herts home page, displaying our carbon progress totaliser, providing more granular detail on our action plan, further develop the hints and tips section of the website and promoting more grants. | ü | ü | ü | ü | ü | ü |  | üü
3.20.2 | Use social media more effectively to encourage behaviour change | 2021-10 | Learnings from May's Forum on Behaviour Change are now being used in our ongoing communications. The Clean Air Day social media campaign in July showed some good improvements with over 11,000 views and 6 times more engagement than other recent East Herts social media posts. Our forthcoming campaigns include Recycling September, COP26, the Queens Canopy, availability of Business Grants and promotion of East Herts' e-vehicles. | ü | ü | ü | ü | ü | ü
3.20.3 | Pursue possibilities to use digital signage in towns with this facility for behaviour change promotion in relation to water, idling et al. | 2021-10 | Taken from suggestion at Environmental Sustainability and Climate Forum. Work with Business Development section for sign locations. Look at joint initiatives with Water Companies. Review frequency of water consumption data KPI metrics. Explore other opportunities for data reporting. Opportunities to be identified, in the first instance, via a meeting with Bishop's Stortford BID Manager in September. |  |  | ü |  |  | ü
3.20.4 | Investigate use of database collected during brown bin change communications. | 2022-01 | The next round of East Herts resident communications will take place in early 2022. Preparation to capture Opt In information is underway. | ü | ü | ü | ü | ü | ü
3.21 | Review heat recovery initiatives in the domestic sector. | 2021-10 | Project is under initial development |  |  | ü | ü |  |  |  | ü
3.32 | Promote COP26 | 2021-10 | A campaign to promote COP26 via a series of local events, festivals and film showings is underway, led by community groups and town/parish councils. East Herts is supporting this activity by connecting people and ideas and providing promotional opportunities. The objective is for all major towns in the district to host some form of sustainability event in the run up to the November COP. A detailed schedule of forthcoming events is available via our website's Get Involved calendar of events. | ü | ü | ü | ü | ü | ü