## 23_24 Action Plan
Updated and reviewed by EHC Carbon and Sustainability Steering Committee and published on website - bi-monthly
Reviewed by attendees of public facing Environmental Sustainability Forum - quarterly
| Environmental Sustainability Actions and timetable | Delivery Year | Accountable Leadership Team officer | Status (See notes for RAG rating)
Action
1 | Make changes to the council's own premises, people and services we deliver
1.1 | Introduce climate change and sustainabilty online training for all officers as part of the mandatory suite of annual training modules | 23/24 | Simon O'Hear Head of HR and Organisational Development
1.2 | All contracts, programmes or one-off expenditure (capital and/or revenue) of £200k+ to have a carbon assessment to inform the decision-making process | 24/25 | Steven Linnett Head of Strategic Finance and Property
1.3 | Include climate change and sustainability awareness in the 2023 member induction programme | 23/24 | James Ellis Head of Legal and Democratic Services
1.4 | Apply to the Public Sector Decarbonisation Scheme in 2023 to enable the installation of a renewable energy heating/hot water source and ancilliary improvements | 23/24 | Jonathan Geall Head of Housing and Health
1.5 | Determine water usage at Wallfields and Buntingford and devise plan for usage reduction | 23/24 | Steven Linnett Head of Strategic Finance and Property
1.6 | Determine whether there is a viable business case for the installation of solar PV panels at Buntingford depot | 23/24 | Jess Khanom-Metaman Head of Operations
1.7 | Procure an e-v charger installation, management and maintenance partner through the Crown Commercial Services framework | 22/23 | Jonathan Geall Head of Housing and Health
1.8 | Determine whether there is a viable business case for the installation of solar canopies at any East Herts Council-owned sites | 24/25 | Jonathan Geall Head of Housing and Health
1.9 | Deliver Hartham Leisure Centre redevelopment to BREEAM Excellent standard | 23/24 | Jess Khanom-Metaman Head of Operations
1.1 | Calculation of carbon emissions from operation of Hartham Leisure Centre | 23/24 | Jess Khanom-Metaman Head of Operations
1.11 | Deliver Hertford Theatre redevelopment to modern energy efficiency standards | 23/24 | Jess Khanom-Metaman Head of Operations
1.12 | Calculation of carbon emissions from operation of Hertford Theatre | 23/24 | Jess Khanom-Metaman Head of Operations
1.13 | Require electric vehicles for street sweepers and up to 3.5 tonne vans and e-v charging infrastructure within the reprocured waste management contract | 23/24 | Jess Khanom-Metaman Head of Operations
1.14 | Assemble a list of East Herts Council land that could be offered for a commercial consideration to developers in pursuit of their biodiversity net gain planning obligations | 23/24 | Jess Khanom-Metaman Head of Operations
1.15 | Enable 6,500 more trees in the district whether through direct provision or partnership working | 23/24 | Jess Khanom-Metaman Head of Operations
1.16 | Complete 23/24 actions associated with HCCSP Plans - Water, Biodiversity, Transport, Carbon, and Behaviour Change once approved. | 23/24 | Jonathan Geall Head of Housing and Health
1.17 | Produce a policy statement on carbon offsetting | 23/24 | Jonathan Geall Head of Housing and Health
1.18 | Establish an annual monitor of offsetting costs at year 2030 | 23/24 | Jonathan Geall Head of Housing and Health
1.19 | Agree a revised East Herts Council risk register regarding adaptation to climate change | 23/24 | Jonathan Geall Head of Housing and Health
1.2 | Publish a revised Air Quality Action Plan | 23/24 | Jonathan Geall Head of Housing and Health
1.21 | Deliver sustainability projects funded through the council's UK Shared Prosperty Fund allocation | 23/24 24/25 | Jonathan Geall Head of Housing and Health
1.22 | Reduce fossil-fuel-based business mileage year-on-year | 23/24 | Steven Linnett Head of Strategic Finance and Property
1.23 | Reduce cloud-based file storage requirement and associated server farm carbon by 25% | 23/24 | Helen Standen Deputy Chief Executive
1.24 | Review the Sustainability Action Plan annually | 23/24 | Jonathan Geall Head of Housing and Health
2 | Use regulatory powers to promote action by others
2.1 | Publish a Vehicle Parking Standards SPD | 24/25 | Sara Saunders Head of Planning and Building Control
2.2 | Publish a revised District Plan which incorporates improved sustainabilty outcomes | 25/26 | Sara Saunders Head of Planning and Building Control
2.3 | Produce a guide for town councils, parish councils and other sub-district bodies in receipt of s106 funding covering sustainability improvements that should be included in any s106-funded capital investment | 23/24 | Ben Wood Head of Communication, Strategy & Policy
2.4 | Support HCC in the installation of at least two rapid e-chargers in support of move to more e-taxis | 24/25 | Jonathan Geall Head of Housing and Health
2.5 | Promote domestic energy efficiency in Houses in Multiple Occupation (HMOs) through the council's HMO licensing responsibilities | 23/24 | Jonathan Geall Head of Housing and Health
3 | Influence and encourage others to do things
3.1 | Support at least 100 households to become more energy efficient in 2023/24 through the provision of grants, loans and/or advice and signposting | 23/24 | Jonathan Geall Head of Housing and Health
3.2 | Using UK SPF monies, employ a community adviser to work with community-led sustainability to promote community-led interventions | 22/23 | Jonathan Geall Head of Housing and Health
3.3 | Reduce the residual waste tonnage per household against the 22/23 baseline | 23/24 | Jess Khanom-Metaman Head of Operations
3.4 | Run at least one multi-media publicity campaign per year, each with identified outcome measures, aimed at encouraging behaviour change on environmental sustainability issues | 23/24 | Ben Wood Head of Communication, Strategy & Policy
3.5 | Champion the council's Environmental Sustainability aspirations at internal member and officer meetings and at external partnership events | 23/24 | Richard Cassidy Chief Executive
3.6 | Publish a Local Cycling and Walking Infrastructure Plan | 23/24 | Sara Saunders Head of Planning and Building Control
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BLUE = not yet due to start GREEN = no identified risk to completion on time AMBER = some risk of non-completion on time, needs some attention RED = significant risk of non-completion on time, needs immediate attention