## Frontsheet
Suggested Topics for Future Forums
The appropriate timing and content of future sessions will take account of the wider programme of development
Date | Topics
August 2024 | · Programme and delivery timeframes
· Estate Charges
· Wider benefits of the development, to be supported by HGGT team
· Roads and Traffic
· Access to Gilston Park – CEMP - timing, location and ensuring accessibility
· Trigger for the health provision
· Benefits to East Herts
· Concern re dead otter found in Gilston Park
April 2024 | · S106 agreement at final draft scrutiny stage
· Master Planning SLMP, V1 & V7
· Roads and traffic management with appropriate persons from Highways at County level present.
· Stewardship, including Biodiversity Net Gain
· Water and Sewage Services to allay concerns of residents by reps from Environment Agency and Affinity Water and Thames Water
· Health Services concerns, with reps from NHS/ICB
FAQ Topic Area | Archaeology
Comms
Current Estate Management
Development Viability
Water, Drainage and Flooding
Ecology and Biodiversity
Education
Garden Town and the wider area
Health
Impact of Development
Items for Future Meetings
Meeting Arrangements
Miscellaneous
Principle of Development
Programme
Review Group Representation
S106
Stewardship
Transport

## tracker
Gilston Area FAQ Tracker
Topic Area | Source | Comment( Key issue, opportunity or Question) | Position
Archaeology | GACF April 2024 | Who is doing the enabling works, such as the archaeology surveys and are these independent? | Yes, the archaeology surveys are independent and both TW and PfP have commissioned the same consultant. All methodologies, assessments and findings were approved by the Herts Archaeology Team at HCC prior to, during and following works. All surveys are undertaken by independent experts and a similar approval process will be followed in future.
Archaeology | GACF April 2024 | Do work plans change if they find anything significant? | Yes, all work stops to ensure appropriate recording and assessment. Designs are changed depending upon the significance of any findings and how this are to be treated.
Comms | GACF April 2024 | There should be a single website which people can subscribe to, so they get emailed about the information. | Please refer to the EH website. You can ask to be placed on a contact list to be advised of further Forum events at community.forum@eastherts.gov.uk
Comms | GACF April 2024 | The last Comments Tracker was issued only a few days ahead. Would like this issued sooner. | Noted and we will endeavour to issue the tracker further in advance of future meetings.
Comms | CF email | Will notes be shared online? | Notes of Forums, highlighting the topics covered, and any actions or commitments made are being shared via this tracker document.
Comms | CF email | Is it possible to join the Forums online? | At the moment, we don’t have plans for online meetings, but have noted this as an engagement preference for consideration for future events.
Comms | GACF April 2024 | Will the questions and answers be shared online and how will community feedback be provided? | This Community Forum Comments Tracker is provided in response, it will be updated after each session. There are other forums for specific feedback on emerging masterplans and proposals.
Comms | GACF April 2024 | We would like the questions addressed as we go. | This Community Forum Comments Tracker is provided in response, it will be updated after each session
Comms | GACF April 2024 | Is the Community Forum for Developers or the Community? | Given that the Community Forum held on 27 February 2024 was the first of its kind, local authority partners felt it was important that EHDC and the developer team both present on the core information regarding the proposals for the Gilston Area. This presentation was comprehensive, given the scale of development proposed, and sought to ensure that those attendees with limited knowledge of the Gilston Area would benefit in future sessions. Significant public question time and discussion was undertaken both before, during and after the presentation, and is planned in future also.
Comms | GACF April 2024 | Turnout today shows you how passionate we are as a community, however, there is a strong sense of mistrust based on previous experience. | All partners in the delivery of the Gilston Area are committed to genuine and meaningful engagement with stakeholders, as well as openness and transparency in the process. Places for People and Taylor Wimpey as the developers for Village 1-6 and 7 are aware how important community engagement is for the emerging proposals and to ensure the development meets local ambition.
Comms | GACF April 2024 | Emails have been sent to several people at PfP with no response. This needs to improve. | Places for People and its appointed project team endeavour to provide detailed and up to date information both proactively and reactively. Contact information is available on the website www.gilstonparkestate.co.uk, where stakeholders can also sign up for updates.
Comms | CF email April 2024 | How will residents be notified of the forum and other activity? | Contact methods will vary depending upon the type of consultation or notification. Digital methods such as emails, websites and parish communications are both time and cost-effective methods of sharing information to a wide audience.
Comms | CF email April 2024 | Why is the forum called the Gilston Area and does not include Eastwick? | The forum name represents the evolution of the major landholding of the application. The name of the forum will evolve further as the site moves into the delivery phase when the site area and individual villages take on their new identities.
Comms | GACF April 2024 | Can PfP and TW deliver joined up comms on traffic disruption in one website and not via the HCC website as this is difficult to use. | In addition to the HCC website, both Taylor Wimpey and Places for People will be notifying residents of any works in advance by publishing this information online at the following address: Gilston Park Estate - Construction Updates. A joint website for construction updates is currently in the build stage.
Comms | CF email | How will residents be notified of traffic and construction works? | All planned highway works are added to the Hertfordshire County Council website: https://www.hertfordshire.gov.uk/services/highways-roads-and-pavements/roadworks-and-road-closures/roadworks-and-road-closures.aspx and the One Network website: https://one.network/uk/hertfordshire All construction affecting highways go through a process of permit approval. Where appropriate advance warning signs will be erected, but these works can be affected by other factors such as adverse weather or emergency road works in the area.
Comms | GACF April 2024 | Harlow Travel Hub is only open on Thurs for limited time in the shopping centre. Can this be extended to several days per week and particularly Saturdays? | At present we do not have sufficient capacity in the resources we have to support longer opening hours. This will be reviewed in future. Contact can, of course, be made with the team through the community.forum@eastherts.gov.uk email address at any time.
Comms | GACF April 2024 | HGGT presentations have not been able to answer any queries about Gilston and how it fits into HGGT. The people the resident spoke to apparently didn't know where Gilston actually is. Can this be fed back to HGGT? | The relationship between the Gilston Area and the wider HGGT development can be the subject of a future Forum.
Current Estate Management | GACF April 2024 | There are land management issues relating to deer. | All estates management issues for Gilston Park Estate should be directed to Gilston@meeting-place.uk, where the project team - including Knight Frank as estates managers - will respond as soon as possible.
Current Estate Management | GACF Sept 2024 | Some of the existing public rights of way across the area are subject to misuse by residents - with dog fouling or lack of adequate supervision of dogs. | Not an issue generated by the new development proposals of course, but subject to current methods of control. These include potential signage, regulation by landowners and enforcement action.
Development Viability | GACF April 2024 | Why has the affordable housing been reduced to 23% from 40%? | The District Plan 2018 (Policy GA1 and HOU3) requires up to 40% affordable housing, subject to viability considerations. The original Gilston Park Estate (GPE) outline planning application (OPA) proposed 40% affordable housing. The application was subject to a viability review in December 2022, which proposed a revised level of 23% affordable housing with an upwards-looking affordable housing review mechanism (AHRM). The December 2022 viability submission explained the reasons and justification for the reduction. Officers and the DMC considered this a reasonable minimum level of affordable housing for the development given the scale and timing of the infrastructure required for delivery of the Gilston Area. The viability submission has also been independently scrutinised by an external consultant on behalf of the EHDC through this process.
Development Viability | GACF April 2024 | What about the viability of other infrastructure? | The infrastructure required to support the Gilston Area was identified as part of the site allocation process and included in the District Plan 2018 (Policy GA1 and GA2). The subsequent Places for People OPA and detailed applications for the Central and Eastern Stort Crossings, and the Taylor Wimpey OPA for Village 7 incorporated this infrastructure, and this included social/community, open space/green and connectivity/utility infrastructure. The infrastructure has therefore been allocated delivery triggers, and the cost and timing of delivery has been taken account of in the subsequent viability appraisals. The viability and delivery of infrastructure to support the Gilston Area is therefore an inherent part of the developments.
Development Viability | GACF April 2024 | When is the viability review date? | The detail of the viability reviews, including the process for review, is to be agreed in the Affordable Housing Review Mechanism which will be detailed in the s106 legal agreement. The HoTs state that there will be at least two reviews for Villages 2, 3, 4 and 6, and one for Village 5. Where there are two reviews, the first will be prior to the first residential reserved matters application (RMA), and the second halfway through RMA approvals. There will only be a review for Village 1 if commencement is delayed by more than three years. Reviews will consider the scheme as a whole on a village by village basis. As above, the draft final text of the full s106 legal agreement will be published online, prior to the agreement being finalised and signed.
Development Viability | GACF April 2024 | How will infrastructure be protected through the viability assessment and in the s106? | The infrastructure will either be directly delivered, or a contribution will be paid to enable its delivery by others. The purpose of the Viability Assessment submitted and approved by EHDC is to ensure there is enough funding available to deliver all the infrastructure (schools, health centre, parks etc) committed to in the s106. The final s106 agreement will confirm the details for infrastructure delivery alongside the development.
Development Viability | GACF April 2024 | How will infrastructure, like GPs be paid for, aside from the housing, and with prices falling across the country? | The infrastructure required to support the Gilston Area, as set out in District Plan policies GA1 and GA2, forms part of the application proposals for the development. The developer is required to fund infrastructure which is required for the development, and this will be secured in the section 106 agreement. The only exception to this is where other organisations (such as Hertfordshire County Council for education) have a legal requirement to fund or supply specific services or types of infrastructure, and this is undertaken through their business planning in accordance with their obligations.
Water, Drainage and Flooding | GACF April 2024 | How will drainage and flooding be managed and in particular, along Fiddler's Brook/Pye Corner? | Places for People are aware that there are existing issues with surface water runoff and localised ponding around the site, including at Gilston Lane/Pye Corner. Places for People have asked their consultant team to review options for mitigating these issues (in the short and/or longer term as appropriate, depending on the severity/extent of the existing issue) and this is being discussed with the LLFA and Environment Agency to help determine an appropriate solution in the context of the development. While the development will increase the amount of impermeable surfaces, planning conditions secure that surface water run-off will be captured across the development site and discharged to existing watercourses at greenfield run-off rates. This will be achieved through the introduction of a range of sustainable drainage (SuDS) features, which will be sized in order to cater for the 1 in 100-year storm event plus an allowance for climate change.
Water, Drainage and Flooding | GACF April 2024 | Flooding at Fiddlers Brook was discussed 3 years ago and remains and issue. What is PfP going to do about this? | Fiddlers Brook is in Flood Zone 3 which means it is and always will be an area that floods. PfP are working alongside the EA, LLFA and Highways to undertake maintenance to the brook within its land. As part of the Outline Planning Application (which requires a s106) a design has been prepared that diverts the main flow of Fiddlers Brook away from the road. PfP are looking to implement this as early as possible (subject to permissions, permits and seasonality). PfP are working with their consultant team to review options for mitigating these issues and this is being discussed with the LLFA and Environment Agency to help determine an appropriate solution in the context of the development, including the STC that connects the proposed Village 1 and Village 2 which are divided by the brook.
Water, Drainage and Flooding | GACF Sept 2024 | Thames Water are known to be in financial difficulty. What would happen if it were to cease trading as a company? What arrangements would be made to ensure drainage and implement improvements required to accommodate the needs of the development? | Whilst the delivery of drainage systems is in the hands of private companies in the country, if any of them were to cease trading it would be necessary for the government to step in with replacement operating arrangements. Such arrangements would need to cover the maintenance of current systems and the programme of improvements already anticipated by the current company.
Water, Drainage and Flooding | GACF 27 Nov 24 | Can the community be given clear assurances that there will be no deterioration in the level of service for existing customers when new development takes place. | Thames Water has a statutory obligation to upgrade systems to accommodate proposed flow increases. The company undertakes frequent reviews of demand and plans investments accordingly.
Water, Drainage and Flooding | GACF 27 Nov 24 | What plans do Thames Water have for Rye Meads Sewage Treatment Works (STW) given development in the Harlow area? Will these be funded wholly or partially from residents? | The industry is funded through the OFWAT price review process. OFWAT sign off the water companies 5 year Asset Management Period (AMP) business plans. The outcome of that determines the costs to be charged to customers across the operating area of the company. 2030). For more information on how the company is funded please refer to the Thames Water website https://www.thameswater.co.uk/about us/regulation/our five year plan
Water, Drainage and Flooding | GACF 27 Nov 24 | Could delivery of the development become dependant on the programme of works by Thames Water without any possibility of recourse to the developers or other funding? | Thames Water will work with developers to understand when further capacity is required. Where appropriate Thames Water will agree phasing of development to coincide with future system upgrades.
Water, Drainage and Flooding | GACF 27 Nov 24 | Have Thames Water the funds to undertake necessary improvements? | Please see information above in relation to Rye Meads STW plans.
Water, Drainage and Flooding | GACF 27 Nov 24 | Can the community be given assurances that there will be no raw waste water discharge into the River Stort as a result of the development in Gilston or the wider Garden Town? | During normal conditions the Rye Meads STW does not discharge untreated waste water to the River Stort. If increased flows from additional properties will exceed the capacity of the STW then upgrades will need to be carried out. During heavy or continued rainfall, storm overflows act as safety mechanism to prevent sewer flooding back into homes and allow the works to continue to operate. When in use, these storm overflows release storm discharge, which is foul flow heavily diluted with rainfall. These are legally permissible under the Environment Agency permit for the works.
Water, Drainage and Flooding | GACF 27 Nov 24 | Does the Rye Meads STW storm overflow, intended to flow into the Stort/ Lea, actually back up and overflow onto adjacent land? What will be the impact of Gilston Area and Harlow development on this? | Please see information above in relation to storm condition overflows.
Water, Drainage and Flooding | GACF 27 Nov 24 | What measures will be implemented to ensure that drainage from current green fields/ undeveloped land not increase and overwhelm drainage systems as the development takes place? | As part of the development proposals a comprehensive Sustainable Urban Drainage (SUDs) system is proposed. This seeks to maximise 'soft' surface water drainage solutions - swales, ponds, infiltration zones etc, and minimise 'hard' solutions - pipes and storage. The overall outcome of the system is that surface water run off from the site is not increased over and above current green field rates. The system builds in a contingency for 'climate change' events. That is increased rainfall or increased intensity of rainfall in future years.
Water, Drainage and Flooding | GACF Oct 25 | Are Affinity Water able to provide supply for an additional 35,000 homes in the area? | Affinity Water (AW) takes a startegic approach to balance supply and demand over the long term. It has a number of significant projects to increase the quantity of water available including diverting water from the SW of the Affinity area where there is excess and the Grand Union Canal project which transfers water from the midlands. The company works with other companies to ensure that these projects do not impact on supply elsewhere. Other projects include reducing consumption, the use of smart meters and the reduction in leaks. By way of constraints, the Environment Agency continues to reduce the amount of water that can be taken through ground water abstraction. AW works over 5 year planning periods and longer term to ensure that demand and supply are matched over the longer term.
Water, Drainage and Flooding | GACF oct 25 | Data Centres are a significant water user, but can the water consumed by these uses be recycled back into further use? | Data Centres use either a closed or open loop approach to their water use. Open loop approach sees the water discharged to drainage systems after use for cooling in the data centre. This can be recycled and reused. The main impediment is the investment required in the necessary infrastructure to enable this, eg water holding, cooling and treatment infrastructure.
Water, Drainage and Flooding | GACF Oct 25 | Are any specific and localised measures required to ensure supply in the Gilston Area? | Demand arising in the Gilston Area is part of the wider demand that Affinity Water (AW) is addressing. The strategic measures referred to above are the approach to ensuring the necessary supply. If any localised works/ infrastructure are required, these will be identified and delivered as the development takes place.
Water, Drainage and Flooding | GACF Oct 25 | What level of contigency is built into demand forecasts and actions? | Affinity Water (AW) always builds in a range of contigency options into future demand projections and infrastructure delivery. This enables fall back options to be implemented if required.
Water, Drainage and Flooding | GACF Oct 25 | Does Affinity Water have the ability to respond to incidents in the system/ provide containment to ensure that there isnt wider impact when supply problems? | Yes, Affinity Water (AW) looks to build in resilience in delivery systems to ensure robustness and resilience.
Water, Drainage and Flooding | GACF oct 25 | Will demand profiles change with the change in the population profile? | This does, to a degree. The company works with overall average demand and consumption across the very broad population profile. It can respond however if that profile and demand changes.
Water, Drainage and Flooding | GACF Oct 25 | Can Affinity Water rely on drawing water from other areas? Don’t those areas also have water stress problems, or will have in the future? | In identifying its programme of supply improvements, Affinity Water works with other water companies to ensure that these do not result in an impact in other water supply areas. It is acknowledged that other areas have water supply impacts and, eg, reservoir levels in the north and west of the country have reduced this year. The company works to a very robust 1 in 500 year drought event.
Ecology and Biodiversity | GACF April 2024 | How can it be a biodiversity net gain (BNG) when the development is building on green belt? | Biodiversity Net Gain (BNG) is an objective measure of the biodiversity value of the land before and after development has taken place. The pre-development value is established through surveys of the land, data from which is inputted to the government's biodiversity metric (or calculator) by qualified ecologists which produces a score. The post-development value is based on the proposals for the land and is also awarded a score, which should be higher - by at least 10% - for the GPE site as a whole. This its then verified and monitored post-completion A minimum 10% net gain can be shown for the GPE site because (a) although the land currently has no development, much of it is used for agriculture/farmland, which has a low biodiversity value, and (b) PfP's proposals involve retaining the areas with high value and enhancing them in addition to creating new areas of biodiversity value. .
Ecology and Biodiversity | GACF April 2024 | Is the site a breeding ground for barn owls, and if so, how will their habitat be protected? | Barn Owl breeding sites have not been confirmed to date within the Gilston Area site, however, they are known to be present in the area during the breeding season. The majority of areas that provide suitable hunting areas for Barn Owl such as rough grassland will be retained and enhanced within the strategic landscape areas, such as the river valley corridors.
Education | GACF April 2024 and GACF May 2025 | How is the delivery of new schools secured? | The s106 will secure the funding for the delivery of new schools in Village 1-6 and Village 7. The s106 Heads of Terms include the number of schools committed to. The developers will have obligations to make payments to Herts CC based on the Department for Education (DfE) costs of new schools at the time. There are occupations restrictions on developers, meaning no more homes can be occupied, if developers do not make these payments and EHDC have powers to enforce the restrictions. There is ongoing liaison between the landowners/ developers and HCC in relation to the design and delivery of schools. The most advanced design is that for the first primary school to be located in Village 1.
Education | GACF Feb 2025 | When will schools and nurseries be provided? | The planning decisions and s106 Agreement require ongoing delivery during the lifetime of the development. First delivery will be the first of up to 7 primary schools. This is planned to open at the start of the first school year (Sept) after the first new residents move into the site.
Garden Town and the wider area | GACF April 2024 | How will the scheme benefit Harlow residents, in terms of housing? There seem to be a lot of impacts to Harlow and not very many benefits. | With regard to housing, the private housing market is, of course, available to all potential house owners regardless of their current location. Additional range and quantity of house types and locations will provide enhanced choice for house purchasers interested in the area. With regard to subsidised affordable housing regulated by the local District Authorities (rather than privately rented properties) East Herts operates an open Housing Register to which any potential resident, regardless of current location, can apply to join. Applications are then considered on the basis of need and agreed published criteria. The privately rented sector provides further opportunities for meeting housing need in the area, regardless of current location. The delivery of further housing provides the opportunity for this sector to also expand. With regard to impacts outside of the Gilston Area and experience in Harlow, this has been suggested for a future topic for the Forum and can be subject to more detailed consideration at such a meeting.
Garden Town and the wider area | GACF April 2024 | Modal shift is welcome - and particularly the new and frequent bus service - but the Harlow bus station works are a problem as the single screen showing arrivals and departures across the bus station has disappeared and you have to walk to each screen for the individual bus stops which is a problem if you are mobility impaired. Can we feed this back to Harlow so everyone can work on modal shift starting now? | Point noted and feedback has been provided to the Harlow councillor responsible for the project.
Health | GACF April 2024 | Will GP services be provided too? | The GPE s106 HoT secures the delivery of a health facility up to a maximum of 3,515sqm, which is to be built to a specification that will be approved by EHDC in consultation with the NHS. The preference is currently for one larger facility in Village 1. The health facility site in Village 1 is to include an ambulance bay. The final s106 agreement will confirm the details for the delivery of the health centre alongside the development. The Herts and West Essex Integrated Care Board (HWE ICB), which is responsible for a significant element of the health services in the area, including GP provision, is best placed to determine the mix of health services that will be provided in a new facility and have been fully engaged in the drafting of the legal agreement.
Health | GACF May 2025 | What is the relationship between the development in the Gilston Area and the redevelopment of the Princess Alexandra Hospital? | Redevelopment of the Princess Alexandra Hospital is the subject of a separate delivery programme led through the health service provider and government agencies. East Herts and Harlow Councils continue to maintain ongoing dialogue to ensure the importance of delivery alongside new residential development is understood.
Impact of Development | GACF April 2024 | How will mitigation to the existing community work? | Mitigation for the existing community to alleviate the impact of development takes several forms. For construction impacts, a series of planning conditions have been agreed to control and manage the process, for example, conditions requiring the agreement of and adherence to a construction traffic and environmental management plan (CTEPM). To alleviate impacts on existing infrastructure, for example, roads, utilities and services, the planning conditions and s106 agreement require the delivery of new or enhanced infrastructure or specific payments to fund service delivery. The s106 will also secure the delivery of new facilities to enable services to be provided such as new schools, primary healthcare facilities and sporting facilities. Places for People may be able to deliver additional mitigation to the existing community, but as this is not required as part of the planning permission, it will be at their discretion.
Impact of Development | GACF May 2025 | How will disruption to the existing community during development be minimised? | Appropriate actions will be considered under the conditional requirements placed on the planning permission and at each stage of the development. Consideration will be given to the location of construction site entrances and construction traffic routes.
Items for Future Meetings | CF email April 2024 | Will there be an opportunity to invite utility providers to the forums such as Affinity Water, Thames Water and the NHS? | The council is considering this request. All utility responses have been considered and reported in the committee reports.
Meeting Arrangements | GACF Sept 2024 | Would it be possible to organise a focussed discussion/ update for residents of the Gilston Park area? | It is understood that some elements of the development will be of more interest to localised areas of residents. It is considered that such localised consultations and discussions would be appropriate when development is planned in detail in relation to individual areas.
Meeting Arrangements | CF email April 2024 | A bigger venue with more parking is preferred | The venue has been changed to the Manor of Groves Hotel.
Miscellaneous | CF email April 2024 | What are enabling works? | Enabling works are the activities required to prepare for the main construction activity. They are required by conditions on the Crossing permissions and can include archaeology assessments, tree removal and boreholes to double check ground conditions for example. As such, they occur at different times with some already having taken place, this has been the reason for the recent roadworks on the A414 and Eastwick Road. The next enabling works will be tree removal to make way for the construction of bridge foundations, which may occur in late autumn 2024.
Miscellaneous | GACF April 2024 | When will the Stortford crossings be delivered? | Not clear what this relates to. There is some detail above in relation to the new and enhanced River Stort crossings.
Miscellaneous | GACF April 2024 | The paper about the CFs on the webpage refers to two appendices (A and B) but these are not on the webpage | Not clear what is being referred to here. If further information can be provided then the documents can be identified.
Miscellaneous | GACF May 2025 | What works have been implemented to Fiddlers Bridge | Minor remedial and restoration works to address handrails/ safety matters.
Miscellaneous | GACF May 2025 | What are meanwhile uses? | Uses which can be introduced on a temporary basis and in temporary locations to meet needs as they become apparent. These can be changed and adapted during the development.
Miscellaneous | GACF May 2025 | How will sustainability matters be addressed as part of the V7 development? | There is a cross site approach to sustainability. So not just in the building construction approach. In that respect the homes will be of a traditional construction. Measures including collective heat generation, green spaces, active travel and biodiversity are proposed.
Principle of Development | GACF April 2024 | How can development be delivered on land which is Green Belt? | The land forming the Gilston Area used to be designated as green belt, however, when the EHDC District Plan was adopted in October 2018, the site was taken out of the green belt and allocated for the development of 10,000 homes and associated development and infrastructure.
Principle of Development | GACF April 2024 | Public Health England are no longer moving to Harlow so do we still have the same housing need at Gilston? | It is not yet finally confirmed whether the relocation of Public Health England (now the UK Health Security Agency (UK HAS)) is to be ceased. Regardless however, the housing need to be delivered is based primarily around the projections of population growth which underpinned the East Herts District Plan (rather than jobs growth). Of course, it is acknowledged that employment opportunities are an important aspect of support to the new and growing communities. East Herts and its Garden Town partners will be working to deliver appropriate employment and economy growth in the Garden Town area regardless of the UK HAS outcome.
Programme | GACF April 2024 and GACF May 2025 | Would like timescales to be provided for the key stages. When will the first home be built? | It is not possible to be precise about when the first homes will be built, but the likely timescale is during 2026-27 with first occupations also in this period. Update in the GACF May 2025. First housing occupations in V1 expected in 2028, with approx. 6 years for build out of V1. The first primary school will be opened the September after the first occupations. More detailed information on timescales, is suggested as a topic to cover at future Forums.
Programme | GACF April 2024 and GACF May 2025 | When will the crossings be open? | It is not possible to be precise about when, but given the trigger required in the s106 (to be finally confirmed) and given housing delivery, it is likely to be during 2028-2029. Timescale for build is likely to be 2 years. 3,250 homes across the Gilston Area is the trigger point for the delivery of the new Eastern Crossing, so quite a way off. This project is a multi-year build so works will start in advance of this.
Programme | GACF April 2024 | What will be the timing of delivery for new infrastructure, for example, providing the first school in time for the first residents? | Considering when infrastructure will be needed to support the development is an inherent part of setting triggers for infrastructure in the s106. The timing of the delivery of infrastructure has been assessed and will be delivered in time to mitigate the impact of the development. The specific timing for the delivery of the schools will be agreed between EHDC, HCC and the developers and obligations in the s106 agreement will control this. The first Primary School will be located in Village 1 and is expected to be open for the September after the first residents move in.
Programme | GACF May 2025 | What size will V1 be? | The upper limit for V1 established in the master plan is 1600 homes. This would require some flatted development. Full details will follow in reserved matters applications.
Programme | GACF May 2025 | Do the government targets for housebuilding have a bearing on what amount of development is delivered at Gilston? | Not directly, the Gilston Area is allocated for 10,000 new homes in the East Herts District Plan. Government targets relate to the delivery of current allocations (inc Gilston) and future Local Plan reviews/ allocations. If development does not come forward on allocated sites, then there is pressure for unallocated land to be promoted for development as the Council has to demonstrate a 5 year supply of land for residential development.
Programme | GACF May 2025 | What is the programme for trenching at Pye Corner? | To an extent this is dictated by the requirements/ availability of the utility providers. Likely to commence in autumn 2025.
Review Group Representation | CF email April 2024 | Will it be possible for local representation such as the NPG or parishes to be on the Review Groups for education and transport and the Shadow Body for stewardship matters? | The Review Groups are technical groups tasked with reviewing monitoring information and they will make recommendations to the relevant authority with the statutory responsibility for decisions. For example, decisions around the opening of new schools or what transport measures are required lay with Hertfordshire County Council. Matters relating to employment floorspace lay with East Herts Council in determining detailed reserved matters applications. There will be community representation in the Shadow Stewardship body once this is established and the S106 agreement sets out the process for the evolution of the shadow body to full stewardship body.
S106 | GACF April 2024 | What is the process for completion of the Section 106 Agreement and what is councillor’s involvement? | East Herts District Council (EHDC) Head of Planning and Building Control has delegated authority granted by the Development Management Committee (DMC) at its meetings in Feb and March 2023 to finalise the detail of the section 106 (s106) legal agreement and draft planning conditions (which were annexed to the DMC officer report), including delegated authority to add to, amend or delete conditions. This is typical for the determination of large applications. Council Members of the DMC have voted on the s106 Heads of Terms, resolving to grant planning permission.
S106 | GACF April 2024 | Will the section 106 HoT be shared online? | The s106 heads of terms (HoT) are already online, appended to the officer report to the 28 February 2023 DMC (Villages 1-6 HoT; Village 7 HoT). In addition, the draft final text of the full s106 legal agreement will be published online, prior to the agreement being finalised and signed.
S106 | GACF April 2024 | When will the S106 agreement be publicly available and for how long? What happens if people make comments on the S106? | The draft S106 agreement will be placed on the application portal before it is completed. The timescale for this and the period prior to completion is not currently confirmed. This is not a consultation exercise so comments are not being invited, but the council will follow necessary procedures in the completion of the legal agreement.
S106 | CF email April 2024 | Who will sign the S106? Is there a clear plan of how it will progress? | The East Herts Head of Planning and Building Control will sign the S106 along with both applicants and a representative from Hertfordshire County Council.
S106 | CF email April 2024 | What is the rationale for the S106? Will the S106 explain why targets in the District Plan such as affordable housing and objectives in the Neighbourhood Plan such as early transfer of the country parks are not met? | The S106 agreement is being drafted in accordance with the Heads of Terms that were reported to the Development Management Committees. These Heads of Terms were arrived at through the consideration of all material policy requirements and stakeholder representations. The rationale for the Heads of Terms were set out in the Committee Reports in detail. There is a balance to be struck between ensuring the viability of all aspects of the development, including transferring an expensive burden to stewardship body in its early stages of development. The S106 agreement does not repeat this rationale.
S106 | GACF May 2025 | Will facilities such as schools and libraries/ other community facilities be provided for the new residents and when? | Yes, there are all secured, along with relevant trigger for provision, in the now completed s106 agreement.
Stewardship | CF email April 2024 and Feb 2025 | What is the timescale for the progress of Stewardship and Governance? | Progress is now required be made on the establishment of the Shadow Stewardship Body following the grant of permission. The first step is the creation of the Shadow Advisory Board, which is required to be set up 3 months after the date of the signing of the s106.
Stewardship | GACF Feb 2025 | How many stewardship organisations will be in place | There will be one overall stewardship organisation for the whole of the Gilston Area. The potential for multiple organisations has been considered, but it was felt this would be less efficient and possibly lead to different standards of delivery.
Stewardship | GACF April 2024 | Why is council tax not being spent on estate management rather than through service charges on new residents? Concerned that residents will have to pay twice. Should be able to reduce council tax for new residents if they are paying a local precept. | It is the case the new residents (and commercial occupiers) will be required to pay a service charge toward to delivery of stewardship arrangements. This will not be the only source of funding for the stewardship body and the charges will be kept to a reasonable level for residents. Residents in existing properties in the Gilston Area and who will have access to the facilities and services provided by the stewardship body will not be required to pay a service charge. The aspiration for stewardship outcomes in the Gilston Area are for substantial areas of public open recreational space, an extensive range of high quality services and facilities, including community provision and sports and leisure facilities. This aspiration has under pinned the proposals for the Gilston Area since the identification of the site through the East Herts District Plan process. It is acknowledged that residents of newly developed properties will pay Council Tax and the new service charge. however, given the range of provision and the intended quality, this is considered reasonable. It is not possible to enable a reduction in normal Council Tax payment levels as new residents will still have access to all services funded and provided through local government arrangements.
Stewardship | GACF Feb 2025 | What will happen in relation to Parish Council precepts? | These will continue to be levied and secured by the Parish Councils. They will be payable by residents through the normal Council Tax approach.
Stewardship | GACF Feb 2025 | What if there insufficient funding for the stewardship organisation? | There will be a range of funding streams, not just the income from service charging. There will also be an endowment from the landowners/ developers, commercial rents and charges for specific services and facilities. One of the actions of the Stewardship Body will be to regularly review its spending and income, look for other future sources of income and ensure that it sets a balanced budget to ensure it is sustainable into the future.
Stewardship | GACF Feb 2025 | How will local community representatives be selected for the Shadow Advisory Body and have the right skills/ capacity and knowledge. What will their roles and responsibilities be. Will they be exposed and accountable if problems occur? | The developer consultants will work with the local community to enable them to feel confident to nominate representatives to the Shadow Body and subsequently to the ongoing Stewardship Body. They will define and explain the roles and responsibilities of the representatives. There will be a degree of accountability as representatives will be expected to properly represent their community. There will be indemnity arrangements in place however so that representatives are appropriately protected.
Stewardship | GACF Feb 2025 | What will be the status of the existing villages and Parish Councils | Currently (Mar 25), the existing Parish Councils remain and continue to operate. In due course, as development starts to take place, different arrangements may be proposed, and will be considered through the appropriate processes at that time. The Parish Councils will continue to operate alongside the Shadow Stewardship Advisory Group as it starts to form.
Stewardship | GACF Feb 2025 | Will there potentially be a conflict of interest for representatives appointed to the Stewardship/ Shadow Body | No. There is a requirement for representatives, when acting in the capacity of the Stewardship/ Shadow Body, to act in the best interests of that body - despite the organisation that they are nominated to represent. This is a routine and expected requirement for representatives on Charitable Trusts and without this arrangement, it would not be possible for representatives of a variety of organisations to come together.
Transport | GACF April 2024 | How will the V7 junction works dovetail with wider works and will V7 communicate their work plans | Co-ordination of works that affect the road networks are tightly controlled by the highway authorities. The V7 team will be able to update on timing of works plans when they are more defined and will also update then on what to expect.
Transport | GACF April 2024 | Will the Sustainable Transport Corridor (STC) be a road? | The Sustainable Transport Corridor (STC) is a route providing active and sustainable travel connectivity between key destinations in the Gilston Area, and across the Harlow and Gilston Garden Town (HGGT). In this way, it will be similar to a road, but will also incorporate green and blue infrastructure such as trees, verges and SuDS, along its length. It will also be used by private cars in some sections, but priority will be given to active and sustainable modes in the design. In a Garden Town context, STCs will connect across the Garden Town to the north, south, east and west, linking key destinations such as the town centre, employment areas and the rail and bus stations.
Transport | GACF April 2024 | When will the STC be built? | Draft planning conditions require that the section of STC entering the Gilston site at Village 1 is delivered before the occupation of any homes in Village 1. Subsequent sections of the STC linking back to this point are to be delivered prior to the occupation of any homes in the village in question. For example, before the occupation of any homes in Village 2, the STC link between the Village 1 Access and Village 2 shall be fully completed and operational. In a Garden Town context, work has begun on the Burnt Mill roundabout to town centre section of the STC and this work is programmed to be completed before Christmas 2025.
Transport | GACF Sept 2024 | Are improvements planned to the existing forecourt and surroundings to the Harlow Town station? | ECC are currently investigating the potential for creating improvements to the public realm in that area and ensuring that adequate circulation and access are maintained.
Transport | GACF Sept 2024 | What evidence is there for the delivery of active and sustainable transport infrastructure in the Gilston Area and connecting with Harlow | Transport modelling which underpinned the allocation of the Gilston Area in the East Herts District Plan modelled a shift in mode choice from the current position to greater use of active/ sustainable modes. Modelling outcomes predicted that, unless a shift of the scale set out in the Transport Strategy was achieved (60% by active/ sustainable modes in the Gilston Area) and a range of traditional transport improvements were implemented (for example the Eastern Crossing) then the highway system would not operate without significant congestion and delay.
Transport | GACF Sept 2024 | What is the current level of journeys undertaken by active/ sustainable means in the Gilston Area | We do not have data specifically for the Gilston Area, but information available for the wider Hertfordshire places this at 36%. This is likely to be much lower in the Gilston Area because of the current lack of active/ sustainable travel opportunities.
Transport | GACF May 2025 | What will the status of the redirected Church Lane in V7 be? How will vehicle speeds be managed? | This is anticipated to become part of the adopted highway. Vehicle speeds to be managed through road design and formal speed limits. Noted that the road accommodates agricultural and other large vehicles.
Transport | GACF May 2025 | When is the signalisation of the Eastwick roundabout junction likely to commence. | Developers are in discussion with HCC in relation to this - earliest commencement likely to be mid 2026.
Transport | GACF Oct 25 | What is the programme for the implementation of the existing Stort Crossing bridge | The programme is to commence works early in 2026. The timescale is dependant on individual elements of the work ad access to work on/ over the rail line.
Transport | GACF Oct 25 | How will the new road over the Stort be implemented. | Anticipated that the new carriageway will be constructed to the west of the existing alignment. Traffic will be transferred to this new carriageway which will then allow the existing carriageway and bridge to be reconfigured/ reconstructed.

## Abbreviations
Key to abbreviations
CEMP | Construction Environment Management Plan
CF | Community Forum
DMC | Development Management Committee
EHDC | East Herts District Council
GACF | Gilston Area Community Forum
HCC | Hertfordshire County Council
HGGT | Harlow and Gilston Garden Town
HoT | Heads of Terms
ICB | Integrated Care Board
NHS | National Health Service
OPA | Outline Planning Application
PfP | Places for People
RMA | Reserved Matters Application
SLMP | Strategic Landscape Master Plan
S106 | Section 106 Agreement (Agreement under s106 of the Town and Country Planning Act)
TW | Taylor Wimpey
V1 | Village One (and other numbered villages: V2, V3 etc)